## Sheet1
ID | Event or Communication | Description© | Purpose | Frequency | Date/Time | Media | Needed Info or Resources | Outgoing Artifacts | Owner | Notes/Comments
1 | Project Kickoff | Kickoff meeting for all internal staekholders | Gain alignment, set ground rules, endorse charter, identify WBS elements and intitial schedule and risks | Once at initiation | 9, 10 September 2020 | Face to face, at corporate HQ with video links to regional centers | Stakeholder Register Charter WBS Template Facilitator Assumptions Log | Signed Ground Rules WBS Draft Risk Register Lessons Learned | Carla Rhee, PM | Ongoing meetings may be virtual - but it is important to have team members meet face-to-face at the project start.
2 | Project Team Meetings | Meeting involving all team members, to discuss the work in-progress / recently completed / coming up | To keep the team informed of the project status and ensure that issues, risks or changes are raised early on. | Weekly | Thursday, 10 AM Central US time | Video conference call | Risk Register Issue Log | Updated Registers and Logs | Bill Lorsch, Deputy PM | Important to track attendance and participation in these meetings, to assure continued engagement.
3 | Issues Meeting | Focused review on top 5 issues | Focused meeting to assure issues are being worked and to get status on issue resolution | Bi-weekly or as urgently needed | Wednesday, 9 AM Central US time | Video conference call, recorded | Issue Log | Updated Registers and Logs | Carla Rhee, PM | Assure a tight connection between the Issue Log and Stakeholder Register.
5 | Executive Review | Monthly reviews by Functional leaders (Product Team, Marketing, Senior Management representatives) | Inform leaders of progress Escalate issues | Monthly | Third Friday of each month | Video conference call with dashboard report | Issue Logs Dashboard report Milestone Charts Heat Maps | Updated Registers and Logs | Carla Rhee, PM | Avoid providing detailed Gantt charts or budget spreadsheets. Stay at the executive stakeholder level.
| Lessons Learned Meeting | Periodic reviews, especially at phase end and project closure | To identify what did and did not go right. Identify areas of improvement | At least at the end of each phase | TBD | Video and in-person | Issue logs, risk report, schedule | Updated lessons learned for repository | Carla Rhee, PM or outside facilitator | As much as possible assure that Lessons Learned are captured as they happen and not only at end of phase or project.
| Project Closure Meeting | Formal meeting held with the Project Board to assess the overall status of the project. | To determine whether the project has been completed and met the final requirements of the customer. | End of project | TBD | Video and in-person | Requirements documentation, closed Issue Log | Signed acceptance letter, or contract document indicating completion, as appropriate. | Carla Rhee, PM | Could be done in conjunction with celebratory event or could be tied to a following such event.